## Phase Overview
Phase | Modules Included | Goal
Phase 1 | Common Foundation + Quiz | Build reusable shared services, then deliver and test the complete Quiz workflow.
Phase 2 | Common Foundation Improvement + Assessment + Final QA | Build the Assessment workflow using shared services, then test the complete platform.

## Simplified Plan
No. | Section | Module | Description | Sub-modules | Dependencies | Phase | Priority | Acceptance Criteria | Status
1 | Common Foundation | User & Role Management | Manage admin/participant access and permissions. | Admin Login; Participant Access; Role Permissions | None — foundational module | Phase 1 | High | Admin can sign in; permissions are enforced; unauthorized access is blocked. | Not Started
2 | Common Foundation | Registration Form Builder | Create a separate configurable registration form for each Quiz or Assessment. | Add/Edit Fields; Required Fields; Response Validation; Save Responses | Depends on User & Role Management | Phase 1 | High | Admin can configure item-specific fields; required fields validate; responses save against the correct item. | Not Started
3 | Common Foundation | Unique Link Management | Generate a separate access/login link for every Quiz and Assessment. | Create Link; Activate/Deactivate Link; Link Validation | Depends on User & Role Management | Phase 1 | High | Each item gets a unique link; active links open the correct item; disabled/invalid links are rejected. | Not Started
4 | Common Foundation | Assignment Rules | Assign the correct Quiz or Assessment using registration answers and admin-defined conditions. | Condition Builder; Match Registration Responses; Assign Item; Assignment Status | Depends on Registration Form Builder and Unique Link Management | Phase 1 | High | Configured conditions assign the correct item; non-matching responses are handled clearly; assignment is recorded. | Not Started
5 | Common Foundation | Participant & Response Data | Store participant profiles, registration responses, assignments, attempts, and status. | Participant Record; Registration Data; Assignment Record; Attempt Record | Depends on User & Role Management | Phase 1 | High | Participant, registration, assignment, and attempt records are linked correctly and protected by permissions. | Not Started
6 | Quiz | Quiz Management | Create and manage quizzes and their settings. | Create/Edit Quiz; Publish/Unpublish; Quiz Instructions; Duration and Attempt Settings | Depends on User & Role Management | Phase 1 | Medium | Admin can create, edit, publish/unpublish, and configure a quiz; changes persist correctly. | Not Started
7 | Quiz | Question Management | Create and organize quiz questions, answer options, correct answers, and marks. | Add/Edit Questions; Options; Correct Answer; Marks; Import Questions (if required) | Depends on Quiz Management | Phase 1 | Medium | Questions, options, correct answers, and marks save correctly and appear in the intended quiz. | Not Started
8 | Quiz | Quiz Registration & Access | Register participants and direct them to the correct quiz using its unique link and assignment rules. | Quiz-Specific Registration Form; Unique Quiz Link; Eligibility/Assignment Check | Depends on Registration Form Builder, Unique Link Management, Assignment Rules, and Participant & Response Data | Phase 1 | High | Registration responses save; the participant can access only the correct quiz when eligible. | Not Started
9 | Quiz | Quiz Attempt & Submission | Let participants attempt the quiz and submit answers reliably. | Instructions; Question Navigation; Timer; Save Answers; Manual Submit; Auto-Submit | Depends on Quiz Management, Question Management, and Quiz Registration & Access | Phase 1 | High | Answers save; timer and submission rules work; duplicate or interrupted submissions are handled safely. | Not Started
10 | Quiz | Quiz Results & Reports | Evaluate answers and provide participant-level and quiz-level results. | Automatic Scoring; Result Summary; Participant Report; Export | Depends on Quiz Attempt & Submission and Question Management | Phase 1 | High | Scores match configured answer keys and marks; reports show correct participant and quiz data; export works. | Not Started
11 | Quiz | Quiz Dashboard | Show quiz activity and progress to admins. | Quiz List; Registration Count; Attempt Status; Completion Status; Results Overview | Depends on Quiz Management, Quiz Registration & Access, and Quiz Results & Reports | Phase 1 | Medium | Counts and statuses match underlying registrations, attempts, completions, and results. | Not Started
12 | Assessment | Assessment Management | Create and manage assessments independently from quizzes. | Create/Edit Assessment; Publish/Unpublish; Instructions; Assessment Settings | Depends on User & Role Management | Phase 2 | Medium | Admin can create, edit, publish/unpublish, and configure assessments independently of Quiz. | Not Started
13 | Assessment | Assessment Question Management | Create and organize assessment questions, sections, marks, and evaluation settings. | Add/Edit Questions; Sections; Marks; Evaluation Settings; Import Questions (if required) | Depends on Assessment Management | Phase 2 | Medium | Assessment questions, sections, marks, and evaluation settings save and display correctly. | Not Started
14 | Assessment | Assessment Registration & Access | Register participants and provide access to the correct assessment using its unique link and assignment rules. | Assessment-Specific Registration Form; Unique Assessment Link; Eligibility/Assignment Check | Depends on Registration Form Builder, Unique Link Management, Assignment Rules, and Participant & Response Data | Phase 2 | High | Assessment-specific registration and link work; assignment eligibility is enforced. | Not Started
15 | Assessment | Assessment Attempt & Submission | Allow participants to complete and submit an assessment. | Instructions; Question/Section Navigation; Timer (if applicable); Save Answers; Submit | Depends on Assessment Management, Assessment Question Management, and Assessment Registration & Access | Phase 2 | High | Answers save; applicable timer and submission rules work; records are linked to the correct assessment. | Not Started
16 | Assessment | Assessment Evaluation & Reports | Evaluate assessment responses and generate assessment-specific reports. | Scoring/Evaluation; Performance Summary; Participant Report; Export | Depends on Assessment Attempt & Submission and Assessment Question Management | Phase 2 | High | Evaluation follows assessment rules; reports and exports show correct assessment data. | Not Started
17 | Assessment | Assessment Dashboard | Show assessment registrations, completion, and performance to admins. | Assessment List; Registration Count; Attempt Status; Completion Status; Performance Overview | Depends on Assessment Management, Assessment Registration & Access, and Assessment Evaluation & Reports | Phase 2 | Medium | Assessment registration, attempt, completion, and performance metrics are accurate. | Not Started
18 | Final QA | Integration & Release Testing | Confirm both modules and common services work together before rollout. | End-to-End Testing; Role/Access Testing; Assignment Rule Testing; Regression Testing; Bug Fixes | Depends on all Common Foundation, Quiz, and Assessment modules | Phase 2 | High | End-to-end and regression tests pass; critical/high bugs are resolved or formally accepted before release. | Not Started

## Project Requirements
ID | Requirement | Description / Rule | Applies To | Validation / Acceptance
REQ-01 | Independent Item Configuration | Each Quiz and each Assessment has its own settings, questions, participants/assignments, and reports. | Quiz & Assessment | Changes to one item do not unintentionally affect another item.
REQ-02 | Unique Access Link | Every Quiz and Assessment has its own unique login/access link. | Quiz & Assessment | Each link opens only its associated item and respects its active status.
REQ-03 | Custom Registration Form | Admin configures a separate registration form for each Quiz/Assessment. | Quiz & Assessment | Each item's configured fields and responses are stored against the correct item.
REQ-04 | Rule-Based Assignment | Registration responses are evaluated against the conditions configured by the admin. | Quiz & Assessment | Matching and non-matching cases behave as configured and are auditable.
REQ-05 | Assessment Without Grade Dependency | Assessment creation, questions, registration, assignment, and reports must not require a Grade system/field. | Assessment | Assessment workflows function when no Grade value or Grade module exists.
REQ-06 | Role-Based Access & Data Isolation | Users can access only permitted features and records. | All Modules | Unauthorized cross-user and unassigned-item access is denied.
REQ-07 | Validation & Error Handling | Show clear errors for duplicate registrations, invalid/expired links, missing required fields, and failed submissions. | All Modules | Errors are clear and data is not silently lost or duplicated.
REQ-08 | Backup & Recovery | Define database backup frequency, retention, restore procedure, and release rollback plan. | Platform / Release | Restore and rollback steps are documented and tested.

## Testing Checklist
Test ID | Module | Test Scenario | Expected Result | Phase | Test Status | Tested By | Comments / Defect ID
TC-01 | User & Role Management | Sign in as admin and participant | Each role sees only permitted screens and actions. | Phase 1 | Not Started
TC-02 | Registration Form Builder | Create different forms for two items | Each form shows its own configured fields and saves responses separately. | Phase 1 | Not Started
TC-03 | Unique Link Management | Open valid, disabled, and invalid item links | Valid link opens the right item; disabled/invalid links are rejected clearly. | Phase 1 | Not Started
TC-04 | Assignment Rules | Submit registration responses that match and do not match conditions | Matching participant is assigned correctly; non-match follows configured behavior. | Phase 1 | Not Started
TC-05 | Participant & Response Data | Check records across two participants and two items | Records remain associated with the correct participant and item; cross-access is blocked. | Phase 1 | Not Started
TC-06 | Quiz Management | Create, edit, publish, and unpublish a quiz | Saved settings persist and published state controls participant access. | Phase 1 | Not Started
TC-07 | Question Management | Add questions, options, answer keys, and marks | Questions and settings display correctly in the intended quiz. | Phase 1 | Not Started
TC-08 | Quiz Registration & Access | Register and open a quiz using its unique link | Registration saves and only eligible participants can access that quiz. | Phase 1 | Not Started
TC-09 | Quiz Attempt & Submission | Save answers, let timer expire, submit twice, and simulate interruption | Answers and submissions are handled according to configured rules without duplicate results. | Phase 1 | Not Started
TC-10 | Quiz Results & Reports | Submit correct, incorrect, and unanswered responses | Scores and report totals match configured answer keys and marks. | Phase 1 | Not Started
TC-11 | Quiz Dashboard | Compare dashboard counts with stored registrations and attempts | Dashboard totals and statuses match the underlying data. | Phase 1 | Not Started
TC-12 | Assessment Management | Create and configure an assessment | Assessment saves independently and does not require a Grade field/system. | Phase 2 | Not Started
TC-13 | Assessment Question Management | Configure assessment questions, sections, and evaluation rules | Assessment content and rules save and display correctly. | Phase 2 | Not Started
TC-14 | Assessment Registration & Access | Register using assessment-specific form and link | Correct form, link, and assignment rules are applied. | Phase 2 | Not Started
TC-15 | Assessment Attempt & Submission | Complete and submit an assessment | Answers, applicable timer, and submission state work correctly. | Phase 2 | Not Started
TC-16 | Assessment Evaluation & Reports | Submit varied responses and export report | Evaluation and report values match configured assessment rules. | Phase 2 | Not Started
TC-17 | Security & Data Isolation | Attempt to open another participant's or unassigned item's data | Access is denied and no unauthorized data is exposed. | Phase 1 & 2 | Not Started
TC-18 | Backup & Deployment | Verify backup and rehearse deployment/rollback steps | Backup can be restored and release can be rolled back using documented steps. | Phase 2 | Not Started
TC-19 | Integration & Release Testing | Run full Quiz and Assessment regression suite | All critical workflows pass and unresolved high-severity defects are documented. | Phase 2 | Not Started